## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
WEBSITE IMPLEMENTATION
Homepage | bar: Week 6; Week 8 to Week 15
Website Information Page | bar: Week 6; Week 8 to Week 15
User Account page/server | bar: Week 8 to Week 15
TESTING
Homepage | bar: Week 6; Week 8 to Week 15
Website Information Page | bar: Week 6; Week 8 to Week 15
User Account page/server | bar: Week 8 to Week 15
DELIVERABLES
Use Cases | bar: Week 6
Requirements | bar: Week 6
website prototype 2 (launched version) | bar: Week 11 to Week 15
website prototype 1 | bar: Week 5 to Week 6; Week 8 to Week 10
SPMP | bar: Week 6